## Summary
Estimate for | Currency Swap
Version | 1.0 | Date | 2016-09-29
Estimated by | Vu Hoang Viet | Reviewed by | Vu Ba Huan
Approved by | Nguyen Quang Vinh
I. Estimates
1. Project Effort
Person Days | 240.8027
Person Months | 1.505
Unit Cost
Final Cost | 0
2. Project Organization
II. Major Milestones
Resource Plan | <Person Amount> | person(s)
Duration Plan | #VALUE! | month(s)
Delivery Date
Requirement
Design
Coding & Unit Test
Component Test
Integration Test
System Test
Acceptance Test
III. Assumption
1. Scope
The following item define scope of software development
Delivery
<Item>
2. Software Development Environment
The following item list all software development & testing environments (programming language, IDE, database tool, OS, ...):
Development Environment
<Item>
Testing Environment
<Item>
3.Proposed Solution
We describe below our proposed solutions (business, technology, ...):
<Item>
4. Out of scope
The estimate does not include the following items:
Item |  | Reason
<Item>
5. Input from Client
The following input are expected to be provided by customer:
Item |  | Date
<Item>
6. On-site resource
There are onsite resources required:
<Item>
Note:
Onsite cost hasn't yet been calculated in the Final Cost
7. Risks
The following items need to be resolved ASAP
<Item>
8. Others
<Item>

## WBS
Work Breakdown Structure
| No | Task Particulars | Complexity | Effort (person-hour) | [8 empty] | Total | Remark
|  |  |  | Requirement | Design | Coding & Unit Test | Test |  |  | Deployment | Support for Acceptance Test
[7 empty] | Component Test | Integration Test | System Test |  |  | Communication and Translation
|  | Development |  | 11.0769 | 11.0769 | 144 | 8.8615 | 8.8615 | 19.9385 | 2.2154 | 4.4308 | 11.0769 | 221.5385
|  | Design |  | 2.7692 | 2.7692 | 36 | 2.2154 | 2.2154 | 4.9846 | 0.55385 | 1.1077 | 2.7692 | 55.3846
| 1 | Database | Average | 0.61538 | 0.61538 | 8 | 0.49231 | 0.49231 | 1.1077 | 0.12308 | 0.24615 | 0.61538 | 12.3077
| 2 | Project Struct | Average | 1.2308 | 1.2308 | 16 | 0.98462 | 0.98462 | 2.2154 | 0.24615 | 0.49231 | 1.2308 | 24.6154
| 3 | Supporting Script | Simple | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 4 | Security Layer | Average | 0.61538 | 0.61538 | 8 | 0.49231 | 0.49231 | 1.1077 | 0.12308 | 0.24615 | 0.61538 | 12.3077
|  | Layout |  | 0.76923 | 0.76923 | 10 | 0.61538 | 0.61538 | 1.3846 | 0.15385 | 0.30769 | 0.76923 | 15.3846
| 5 | UI Layout Frame | Average | 0.61538 | 0.61538 | 8 | 0.49231 | 0.49231 | 1.1077 | 0.12308 | 0.24615 | 0.61538 | 12.3077
| 6 | Menu/Navigation | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
|  | Users |  | 4.1538 | 4.1538 | 54 | 3.3231 | 3.3231 | 7.4769 | 0.83077 | 1.6615 | 4.1538 | 83.0769
| 7 | Login/Logout | Average | 0.92308 | 0.92308 | 12 | 0.73846 | 0.73846 | 1.6615 | 0.18462 | 0.36923 | 0.92308 | 18.4615
| 8 | Register | Average | 0.61538 | 0.61538 | 8 | 0.49231 | 0.49231 | 1.1077 | 0.12308 | 0.24615 | 0.61538 | 12.3077
| 9 | User Profile & Avatar | Average | 0.92308 | 0.92308 | 12 | 0.73846 | 0.73846 | 1.6615 | 0.18462 | 0.36923 | 0.92308 | 18.4615
| 10 | Approve Registered User | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 11 | User Tabs | Simple | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 12 | User List | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 13 | Save Action | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 14 | Forget Password | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 15 | Auto Block User when Date Expired | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
|  | Orders |  | 1.8462 | 1.8462 | 24 | 1.4769 | 1.4769 | 3.3231 | 0.36923 | 0.73846 | 1.8462 | 36.9231
| 16 | New Order | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 17 | Search Matching Orders | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 18 | Submit Action | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 19 | Swap Action | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 20 | Order Details | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 21 | Activity Logs | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 22 | Confirm Action | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 23 | Cancel Action | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 24 | Clear Action | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 25 | Order Tabs: Working Orders, Submited Orders, History | Simple | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
|  | Support |  | 0.61538 | 0.61538 | 8 | 0.49231 | 0.49231 | 1.1077 | 0.12308 | 0.24615 | 0.61538 | 12.3077
| 26 | Support Form | Average | 0.23077 | 0.23077 | 3 | 0.18462 | 0.18462 | 0.41538 | 0.046154 | 0.092308 | 0.23077 | 4.6154
| 27 | Help |  | 0.076923 | 0.076923 | 1 | 0.061538 | 0.061538 | 0.13846 | 0.015385 | 0.030769 | 0.076923 | 1.5385
| 28 | Support Message Management |  | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
|  | Notification |  | 0.92308 | 0.92308 | 12 | 0.73846 | 0.73846 | 1.6615 | 0.18462 | 0.36923 | 0.92308 | 18.4615
| 29 | Quick View | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 30 | Full View | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 31 | Notification on All actions | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
|  | Management | [10 empty] | 19.2642
| 1 | PM | [10 empty] | 12.0401
| 2 | CM | [10 empty] | 2.408
| 3 | Contract Management | [10 empty] | 2.408
| 4 | Training | [10 empty] | 0
| 5 | Quality Control | [10 empty] | 2.408
|  | Total | [10 empty] | 240.8027
Norm Reference
|  |  | Percent | Remark
| Development |  | 100%
| Requirement |  | 5%
| Design |  | 5%
| Coding & Unit Test |  | 65%
| Component Test |  | 4%
| Integration Test |  | 4%
| System Test |  | 9%
| Deployment |  | 1%
| Support for Acceptance Test |  | 2%
| Communication and Translation |  | 5%
|  |  | Percent | Remark
| Overhead Management |  | 100%
| Development |  | 92%
| PM |  | 5%
| CM |  | 1%
| Contract Management |  | 1%
| Training |  | 0%
| Quality Control |  | 1%

## Record of change
Record of change
Effective Date | New Version | Changed Item | Change description | Reason for Change | Reference
29/09/2016 | 1.0 | Initial