## Summary
Estimate for | Currency Swap
Version | 1.0 | Date | 2016-09-29
Estimated by | Vu Hoang Viet | Reviewed by | Vu Ba Huan
Approved by | Nguyen Quang Vinh
I. Estimates
1. Project Effort
Person Days | 240.8027
Person Months | 1.505
2. Project Organization
II. Major Milestones
Resource Plan | <Person Amount> | person(s)
Duration Plan | #VALUE! | month(s)
Delivery Date
Requirement
Design
Coding & Unit Test
Component Test
Integration Test
System Test
Acceptance Test
III. Assumption
1. Scope
The following item define scope of software development
Delivery
<Item>
2. Software Development Environment
The following item list all software development & testing environments (programming language, IDE, database tool, OS, ...):
Development Environment
OS: Linux
IDE: Visual Studio Code
DBMS: MySQL
NodeJS
Testing Environment
OS: Ubuntu Server 16.04
DBMS: MySQL
NodeJS
3.Proposed Solution
We describe below our proposed solutions (business, technology, ...):
NodeJS for server-side. Jquery UI with reponsive design support for web front-end.
MySQL for DBMS
We recommend to deploy entire system on Amazon Web Services (AWS) with following configurations:
Server: 01 instance of t2.micro (01 GB of RAM, 01 CPU, 8 GB of SSD)
DB: Amazon RDS, 01 instance, MySQL 5.6.
Note that the configurations above are eligible to Free Tier of Amazon, applicable for new account in the first 12 months
4. Out of scope
The estimate does not include the following items:
Item |  | Reason
5. Input from Client
The following input are expected to be provided by customer:
Item |  | Date
Specification, Wireframe
6. On-site resource
There are onsite resources required:
Note:
Onsite cost hasn't yet been calculated in the Final Cost
7. Risks
The following items need to be resolved ASAP
8. Others

## WBS
Work Breakdown Structure
| No | Task Particulars | Complexity | Effort (person-hour) | [8 empty] | Total | Remark
|  |  |  | Requirement | Design | Coding & Unit Test | Test |  |  | Deployment | Support for Acceptance Test
[7 empty] | Component Test | Integration Test | System Test |  |  | Communication and Translation
|  | Development |  | 11.0769 | 11.0769 | 144 | 8.8615 | 8.8615 | 19.9385 | 2.2154 | 4.4308 | 11.0769 | 221.5385
|  | Design |  | 2.7692 | 2.7692 | 36 | 2.2154 | 2.2154 | 4.9846 | 0.55385 | 1.1077 | 2.7692 | 55.3846
| 1 | Database | Average | 0.61538 | 0.61538 | 8 | 0.49231 | 0.49231 | 1.1077 | 0.12308 | 0.24615 | 0.61538 | 12.3077
| 2 | Project Struct | Average | 1.2308 | 1.2308 | 16 | 0.98462 | 0.98462 | 2.2154 | 0.24615 | 0.49231 | 1.2308 | 24.6154
| 3 | Supporting Script | Simple | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 4 | Security Layer | Average | 0.61538 | 0.61538 | 8 | 0.49231 | 0.49231 | 1.1077 | 0.12308 | 0.24615 | 0.61538 | 12.3077
|  | Layout |  | 0.76923 | 0.76923 | 10 | 0.61538 | 0.61538 | 1.3846 | 0.15385 | 0.30769 | 0.76923 | 15.3846
| 5 | UI Layout Frame | Average | 0.61538 | 0.61538 | 8 | 0.49231 | 0.49231 | 1.1077 | 0.12308 | 0.24615 | 0.61538 | 12.3077
| 6 | Menu/Navigation | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
|  | Users |  | 4.1538 | 4.1538 | 54 | 3.3231 | 3.3231 | 7.4769 | 0.83077 | 1.6615 | 4.1538 | 83.0769
| 7 | Login/Logout | Average | 0.92308 | 0.92308 | 12 | 0.73846 | 0.73846 | 1.6615 | 0.18462 | 0.36923 | 0.92308 | 18.4615
| 8 | Register | Average | 0.61538 | 0.61538 | 8 | 0.49231 | 0.49231 | 1.1077 | 0.12308 | 0.24615 | 0.61538 | 12.3077
| 9 | User Profile & Avatar | Average | 0.92308 | 0.92308 | 12 | 0.73846 | 0.73846 | 1.6615 | 0.18462 | 0.36923 | 0.92308 | 18.4615
| 10 | Approve Registered User | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 11 | User Tabs | Simple | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 12 | User List | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 13 | Save Action | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 14 | Forget Password | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 15 | Auto Block User when Date Expired | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
|  | Orders |  | 1.8462 | 1.8462 | 24 | 1.4769 | 1.4769 | 3.3231 | 0.36923 | 0.73846 | 1.8462 | 36.9231
| 16 | New Order | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 17 | Search Matching Orders | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 18 | Submit Action | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 19 | Swap Action | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 20 | Order Details | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 21 | Activity Logs | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 22 | Confirm Action | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 23 | Cancel Action | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 24 | Clear Action | Average | 0.15385 | 0.15385 | 2 | 0.12308 | 0.12308 | 0.27692 | 0.030769 | 0.061538 | 0.15385 | 3.0769
| 25 | Order Tabs: Working Orders, Submited Orders, History | Simple | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
|  | Support |  | 0.61538 | 0.61538 | 8 | 0.49231 | 0.49231 | 1.1077 | 0.12308 | 0.24615 | 0.61538 | 12.3077
| 26 | Support Form | Average | 0.23077 | 0.23077 | 3 | 0.18462 | 0.18462 | 0.41538 | 0.046154 | 0.092308 | 0.23077 | 4.6154
| 27 | Help |  | 0.076923 | 0.076923 | 1 | 0.061538 | 0.061538 | 0.13846 | 0.015385 | 0.030769 | 0.076923 | 1.5385
| 28 | Support Message Management |  | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
|  | Notification |  | 0.92308 | 0.92308 | 12 | 0.73846 | 0.73846 | 1.6615 | 0.18462 | 0.36923 | 0.92308 | 18.4615
| 29 | Quick View | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 30 | Full View | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
| 31 | Notification on All actions | Average | 0.30769 | 0.30769 | 4 | 0.24615 | 0.24615 | 0.55385 | 0.061538 | 0.12308 | 0.30769 | 6.1538
|  | Management | [10 empty] | 19.2642
| 1 | PM | [10 empty] | 12.0401
| 2 | CM | [10 empty] | 2.408
| 3 | Contract Management | [10 empty] | 2.408
| 4 | Training | [10 empty] | 0
| 5 | Quality Control | [10 empty] | 2.408
|  | Total | [10 empty] | 240.8027
Norm Reference
|  |  | Percent | Remark
| Development |  | 100%
| Requirement |  | 5%
| Design |  | 5%
| Coding & Unit Test |  | 65%
| Component Test |  | 4%
| Integration Test |  | 4%
| System Test |  | 9%
| Deployment |  | 1%
| Support for Acceptance Test |  | 2%
| Communication and Translation |  | 5%
|  |  | Percent | Remark
| Overhead Management |  | 100%
| Development |  | 92%
| PM |  | 5%
| CM |  | 1%
| Contract Management |  | 1%
| Training |  | 0%
| Quality Control |  | 1%

## Record of change
Record of change
Effective Date | New Version | Changed Item | Change description | Reason for Change | Reference
29/09/2016 | 1.0 | Initial