## Sumary
Version 1.1
2016-10-07
VietSoftware International
CURRENCY SWAP

## Change
History
No. | Create | Version | Date | Description
1 | Nguyễn Danh Tháp | Version 1.0 | 2016-10-07
2 | Nguyễn Danh Tháp | Version 1.1 | 2016-10-07

## Schedule
1. Schedule
[21 empty] | : | Holiday |  |  |  |  | ▼ | : Demo | [8 empty] | : | Timeline Testing | [7 empty] | : | Timeline UAT
[20 empty] | : | Timeline Sprint 1 | [6 empty] | : | Timeline Sprint 2 | [7 empty] | : | Timeline Release 1 | [7 empty] | : | Release
| Currency Swap |  |  |  | 2016-10-01 | [18 empty] | 2016-11-01
 | time axis 2016-10-13 to 2016-12-05
Requirements and environment | bar: 2016-10-13 to 2016-10-14; 2016-11-05 to 2016-11-06; 2016-11-12 to 2016-11-13; 2016-11-19 to 2016-11-20; 2016-11-26 to 2016-11-27; 2016-12-03 to 2016-12-04
Demo Sprint 1 | bar: 2016-10-17 to 2016-10-21; 2016-10-24 to 2016-10-28; 2016-10-31; 2016-11-05 to 2016-11-06; 2016-11-12 to 2016-11-13; 2016-11-19 to 2016-11-20; 2016-11-26 to 2016-11-27; 2016-12-03 to 2016-12-04
Demo Sprint 2 | bar: 2016-11-01 to 2016-11-14; 2016-11-19 to 2016-11-20; 2016-11-26 to 2016-11-27; 2016-12-03 to 2016-12-04
Release 1 | bar: 2016-11-05 to 2016-11-06; 2016-11-12 to 2016-11-13; 2016-11-15 to 2016-11-21; 2016-11-26 to 2016-11-27; 2016-12-03 to 2016-12-04
Testing | bar: 2016-10-31 to 2016-11-21; 2016-11-26 to 2016-11-27; 2016-12-03 to 2016-12-04
UAT | bar: 2016-11-05 to 2016-11-06; 2016-11-12 to 2016-11-13; 2016-11-19 to 2016-11-20; 2016-11-22 to 2016-12-05
Release | bar: 2016-11-05 to 2016-11-06; 2016-11-12 to 2016-11-13; 2016-11-19 to 2016-11-20; 2016-11-26 to 2016-11-27; 2016-12-03 to 2016-12-05
2. Note
|  | Requirements & Environment | 2016/10/13~ 2016/10/14
- Requirement Analystic
- Project configuration
|  | Demo Sprint 1 | 2016/10/31
Design
Database
Project Struct
Supporting Script
Security Layer
Layout
UI Layout Frame
Menu/Navigation
Users
Login/Logout
Register
User Profile & Avatar
Approve Registered User
User Tabs
User List
Save Action
Forget Password
Auto Block User when Date Expired
Demo Sprint 2
2016/11/07
Orders
New Order
Search Matching Orders
Submit Action
Swap Action
Order Details
Activity Logs
Confirm Action
Cancel Action
Clear Action
Order Tabs: Working Orders, Submited Orders, History
2016/11/14
Support
Support Form
Help
Support Message Management
Notification
Quick View
Full View
Notification on All actions
|  | Release 1 | 2016/11/21
|  | Testing | 2016/10/31~2016/11/21
|  | UAT | 2016/11/22~2016/12/05
|  | Release | 2016/12/05