## Tracking task
Item | Rule tracking
Schedule Management | 1- Master Plan is developed. - Include: File Excel. - Saved: GIT
2- Team member has tasks as assigned Each member has at least 1 In-progress Task before daily meeting ( before 8h55')
3- Engineering task is filled with Assignee, Original estimate, Due date, Subtask type
4- Tasks are up-to-date Mandatory fields to update: + Story: Status, Assignee,Story point + Detail task: Status, Duedate, Assignee, Remaining Time, Time spent
5- After planning meeting, task list has created on Redmine ( QA check sau 0.5 Day)
6- Review task ( source code) has created on Redmine after finish coding?
Effort Management | Project Team logs Timesheet of assigned task ( before 10a.m daily) 1- 4h/ ngày: a Tháp, a Huấn 2- 8h/ngày: a Việt Bin, Anh Công, Long ( Công và Long đi học JP thì cần inform trong daily meeting để QA biết còn check. Không inform gì mặc định là full 8h)
Communication Management | Team meeting is conducted as frequency ( at 9:30)

## Process
PO |  | PM | Dev | TL
NOK
OK
[5 empty] | PM | Dev
Được khởi tạo trong vòng 0.5Day sau planning
Được tạo khi task kế trước Closed
* Để thuận tiện cho việc filter và thống kê dữ liệu, Subject phải được viết theo đúng Naming convention với [Prefix] như trên
User Story
Tạo AT
Review AT
Coding & run AT
Review source code
( tạo sau khi finish coding)
Send Requirement
Study Requirement
Create AT
Coding
Merge code
Release
Review AT
Review code
NOK
OK
repeat with all sprint
Demo
UAT
NOK
OK
NOK
End
OK
Start
Execute AT
User Story
[AT]...mô tả...
[Review AT]...mô tả...
[Coding]...mô tả...
[Run AT]...mô tả...
[Review code]...mô tả...
[Merge code]...mô tả...
[Training]...mô tả...